ERATEX DJAJA TBK Solution Presentation Crux Manufacturing Flow-Control & OTIF Improvement Programme Prepared by Vector Consulting Group ¦ June 2026

This document distils the strategic crux of the Eratex Solution Deck — a 299-slide proposal by Vector Consulting Group — into a single reference that captures the problem thesis, root-cause chain, solution architecture, and expected impact. It is intended for use in planning, alignment, and scoping conversations.

# 1.  The Central Thesis

The presentation is built around a single, unambiguous proposition:

Eratex can become a preferred supplier only if it delivers high OTIF consistently — on originally committed dates, within customer-accepted lead times — without relying on firefighting, overtime, excess inventory, or management follow-up.

The deck argues that Eratex currently measures performance against revised dates with a 1–2 day leeway, which creates an illusion of reliability. True customer reliability — measured against the first commitment and including full-quantity delivery — is significantly weaker. The solution path is a system-driven operating model governed by plant reality, not by manual judgement and firefighting.

# 2.  Business Context

## 2.1  The Commercial Imperative

Sales and gross contribution have grown only marginally at Eratex while costs continue rising. The lever available is customer attractiveness: becoming a reliable preferred supplier to grow revenues and protect margins without proportionate cost increases.

The deck defines what customers require from a preferred supplier:

- On-time delivery against the originally committed date

- In-full quantities — no short shipments

- Delivery within the customer's expected lead-time window

- Consistent quality as a hygiene requirement, not a differentiator

## 2.2  Vector Consulting Group's Engagement Model

The deck positions Vector as an implementation-oriented operations flow management firm, not an advisory-only consultant. The proposed engagement model is:

- Build-Operate-Transfer: Vector builds the system and operating model, operates it through stabilisation, and transfers capability to Eratex teams

- Software tools developed by Vector Digital Labs, customised to Eratex

- Fees partially linked to performance improvement outcomes

- Sustenance through SOPs, KRAs, functional champions, process audits, dashboards, and training

# 3.  Current Performance Reality

The presentation exposes a systematic gap between the performance Eratex reports internally and what customers actually experience.

| Metric | Current | Context |
| --- | --- | --- |
| On-Time Delivery (OTD) — lenient measure | ~95% | 1–2 day leeway on revised ex-factory date |
| In-Full (IF) performance | 75–85% | 15–25% of orders short-shipped each month |
| OTIF — on-time AND in-full | 75–80% | Both conditions combined; drops 15–20pts |
| OTIF — against first commitment | 65–75% | What customers actually experience |
| Orders with lead time > 130 days | 30–40% | Preferred suppliers must fit customer LT window |
| FKD OTIF (Full Kit Date) | 80–90% | Calculated on revised FKD, not original |
| Laundry idle time (daily average) | ~25% | Scheduling gaps, lots not ready |
| Laundry shift plan adherence | ~50% | Non-adherence driven by WIP, machines, sequencing |
| Sewing line changes (week-over-week) | 25–31% | Feb 2026 data; 266–337 changes per week |

The critical insight: performance measured against internally revised dates masks genuine unreliability. Customers measure against the first date they were given. That gap — between the internal revised-date view and the customer’s first-commitment view — is where preferred-supplier status is won or lost.

# 4.  Root Cause Chain: Why OTIF Is Low

The deck organises unreliability into four compounding failure areas. These are not independent; each failure layer amplifies the next.

| Failure Area | Root Causes | Business Impact |
| --- | --- | --- |
| FKD Failures (Full Kit Date) | Delays in fabric, trims, or PPS/sample approval. Visibility fragmented across emails, trackers, and WhatsApp. Person-dependent follow-up. Different priorities across departments. Incomplete handovers. | Materials/approvals not ready when cutting must start. Every FKD miss compresses the production window or forces PCD revision. |
| PCD Instability (Planned Cut Date) | PCD dates revised repeatedly — pull-aheads, postponements, shifts. Teams start everything early because they cannot see what will become urgent next, creating priority conflict and high WIP. | Actual cut adherence far worse than the apparent 5–10% miss rate. Expediting pressure builds across pre-production. |
| Resource Overload (Planning Mismatch) | Planning level-loads one department while unknowingly overloading another. Critical sub-resources (specific wash machine groups, sewing line types) are not checked individually at plan time. | Plans appear valid but are unrealisable. Laundry wet-process capacity exceeded in peak weeks. Sewing, cutting, finishing load imbalances. |
| Execution Instability (Sewing & Laundry) | Frequent sewing line reassignments and sewing start date changes (25–31% of orders per week). Laundry manually scheduled with complex routing, batch, and machine constraints. | Sewing efficiency loss. Capacity erosion month-over-month. Laundry has ~25% idle time and ~50% schedule non-adherence. Expediting mandatory. |

## 4.1  The Consequence Chain

These four failure areas cascade directly into business costs and bandwidth loss:

- Overtime costs: $1.3M–$1.9M per quarter (Q1–Q2 2025 data)

- Outsourcing costs: $0.1M–$0.23M per quarter

- Air freight and customer penalties: 100% addressable per the proposal

- Finished goods inventory buildup from pre-ponement: WC lock and operational clutter

- Fabric inventory >40 days at warehouse; 5+ days dead stock from cancellations

- Management bandwidth consumed by daily firefighting, leaving no capacity for quality and process improvement

- Sewing capacity loss compounding month-over-month as reshuffling lowers line efficiency

# 5.  Project Objective

ERATEX must establish system-driven operations while achieving OTIF > 95% consistently — on originally committed dates, within customer-accepted lead times — with zero dependence on firefighting.

The objective is explicitly broader than a scheduling improvement. It covers:

- Reliability on originally committed dates, not revised dates

- Full-quantity delivery on every order

- Lead times within customer-accepted windows

- Release of merchandising, procurement, production, and management bandwidth

- Elimination or drastic reduction of overtime, outsourcing, air freight, and penalties

- Reduction of fabric and trim inventory without increasing risk

# 6.  Solution Architecture

The proposed solution is an integrated manufacturing flow-control operating model. It is not a standalone scheduling tool. It connects planning, readiness, execution, and governance into a closed loop.

## 6.1  Plan in Three Zones

The horizon before ex-factory is divided into three governance zones:

| Zone | Purpose | Governance Rule |
| --- | --- | --- |
| Future Zone | Predict a reliable delivery week based on projected load ahead of all critical resources | System-suggested date based on load. No manual commitment without load check. |
| Volatile Zone | Order confirmation and strategic prioritisation. MD retains flexibility to shift or reprioritise orders. | Rejigging allowed. Visibility of load impact required before changes. |
| Firm Zone | Fixed due dates. Orders scheduled on sewing lines. Execution against the frozen plan. | Plan changes after freeze governed by escalation. Delays absorbed in execution via buffer priorities, not replanning. |

## 6.2  Capacity-Constrained Order Commitment

Every order commitment must be validated against all critical resource sub-categories before a delivery date is quoted to the customer. The order loading tool:

- Takes inputs: SMV, route, laundry routing, demanded delivery week, existing load chart

- Checks load against each critical resource sub-category (not just department totals)

- Suggests alternate delivery weeks if the demanded week is overloaded

- Prevents manual commitment outside system-calculated feasibility

## 6.3  Critical Resource Sub-Categories

The deck insists that planning must check sub-categories, not only department-level capacity, because orders can only run on specific resource subsets:

- Sewing sub-categories: AMEO Basic, GU Basic, AT Basic, CK Basic, Levis Basic — a basic 5-pocket order cannot be loaded against all sewing capacity

- Laundry wet-process sub-categories: Tonello 125kg, Tonello 150kg, Brongo, Yilmax, Tolkar, Ramson, PP Spray Booth, Mannequin — wash orders are machine-specific

- Other critical resources tracked: Cutting, Relaxation, Embroidery/Printing, Finishing, RM Store, FG Warehouse

## 6.4  Freeze the Plan and Absorb Delays in Execution

The current model treats every delay as requiring a plan change, which perpetuates instability. The proposed model separates:

- Delays that can and should be absorbed in execution through buffer priority management

- Genuine shocks that require controlled replanning with governance approval

A frozen plan is protected. Execution works against it. The plan is not reshuffled for every operational disturbance.

## 6.5  Buffer-Based Priority System for Execution

All work centres and teams operate from a single priority signal based on buffer consumption:

| Priority | Buffer Condition | Action |
| --- | --- | --- |
| BLACK | Buffer fully consumed or overrun | Highest priority. Immediate escalation. Daily Flow Meeting focus. |
| RED | More than two-thirds buffer consumed | High priority. DFM tracking. Reason code capture. |
| YELLOW | One-third to two-thirds buffer consumed | Monitor closely. Prevent further slippage. |
| GREEN | Less than one-third buffer consumed | Normal execution. No special action. |
| WHITE | No buffer consumed | Lowest priority. Capacity available to pull forward. |

## 6.6  Daily Flow Meeting

A structured daily meeting to manage elapsed time after order release into production:

- Fixed time, fixed place, fixed participants, and a designated DFM champion

- Focuses on BLACK and RED priority orders only — no general status reporting

- Covers FKD adherence, PCD adherence, and production alignment

- Tracks multi-line order basket completion and elapsed time between first and last line completion

- Records remarks, reason codes, and resolution actions for every escalated order

## 6.7  Laundry Daily Scheduler

Laundry is the most constrained and complex operation in the plant. It has variable routing per CMT/order, shifting bottleneck machines, both piece-based dry processes and lot-based wet processes, batch formation requirements, and customer-machine preferences. A dedicated scheduler is proposed with the following logic:

- Machine-wise, order-wise, and operation-wise sequencing

- Bottleneck loading — keep the constraint machine from starving

- CMT changeover minimisation within shifts

- Batch formation respecting lot availability and machine group constraints

- Stage-wise WIP status tracking as scheduler input

- Capacity calendar including planned maintenance and holidays

- Refreshes daily with updated WIP, lot status, and machine availability

## 6.8  Workflow Automation for Merchandising and Pre-Production (TMS/WAS)

The deck argues that production planning and execution improvements alone cannot deliver high OTIF if merchandising and pre-production activities — the sources of FKD and PCD failures — continue operating through fragmented emails, WhatsApp, and manual trackers.

The proposed Workflow Automation System (TMS/WAS) operates as follows:

- All activities for every project are pre-loaded on a single platform with predefined sequences

- Tickets open only when prerequisites are complete and the resource can actually start work

- Ticket closure requires mandatory inputs (dates, PO numbers, checklists, file uploads) — no yes/no closure

- Workflow templates are defined by customer, fabric type, and garment type

- Priority is driven by two factors: SLA breach (ticket-level) and buffer penetration against FKD/PCD (project-level)

- Documents uploaded to tickets are retained in a central repository accessible throughout the project

- API integration with Eratex's existing systems (Datatex, ERP) prevents duplicate manual data entry

- Project initiation triggered by email-based order notifications, not dependent on manual ERP status changes

## 6.9  Vector Flow and FastReact Integration

The proposed tool architecture separates the planning logic layer from the scheduling visualisation layer:

- Vector Flow carries the core allocation and calculation logic: which sewing sub-category, how many lines, which lines, load against all critical resources, due-date feasibility, priority reports, dashboards

- FastReact operates in auto mode — as a planning visualisation and plan-holding board — fed by Vector Flow outputs

- Datatex supplies confirmed and projected order data into the system

- Manual overrides in FastReact are explicitly discouraged because they create drift between FastReact's plan and Vector Flow's load calculation, causing daily due-date changes and preventing plan stability

## 6.10  POOGI: Process of Ongoing Improvement

Every order that turns RED triggers a reason-code capture. Reason codes are aggregated monthly into a Pareto analysis, which drives targeted improvement projects:

- Machine breakdowns

- Setup reduction

- Quality failures

- Coordination failures

The sustenance model includes: IT tools, SOPs, KRAs, functional champions, process audits, dashboards, and structured training. Dashboards cover OTIF, lead time, FG spread, merchandising priorities, pre-production priorities, cutting WIP, sewing, and laundry.

# 7.  Proposed Tool Landscape

| Tool | Primary Role | Key Interfaces |
| --- | --- | --- |
| Vector Flow | Core planning & execution-control logic: load calculation, date quotation, priority reports, dashboards, sewing scheduler | FastReact (outputs), Datatex (inputs), TMS/WAS |
| FastReact | Sewing plan visualisation and scheduling board in auto mode using Vector Flow inputs | Vector Flow (receives plan), Datatex (order data) |
| Datatex / ERP | Authoritative source for order data, quantities, dates, and status transitions | Vector Flow, TMS/WAS, FG/RM systems |
| TMS / WAS | Workflow automation for merchandising and pre-production: project creation, ticketing, SLA, file repository, API pull | Email triggers, Datatex/ERP APIs, document store |
| Laundry Scheduler | Daily constraint-machine scheduling for laundry operations: batching, sequencing, bottleneck loading | Vector Flow, shop-floor WIP systems |
| Dashboards | Management review layer: OTIF, lead time, FG spread, priority management, WIP visibility, POOGI Pareto | Vector Flow, TMS/WAS, ERP |

# 8.  Expected Benefits

These are proposal targets and business-case assumptions presented in the deck. They have not been validated as achieved results and should be treated as planning references.

| Benefit | Target |
| --- | --- |
| OTIF — on originally committed dates | > 95% |
| FKD and PCD adherence | > 95% |
| Year-on-year sales increase | 6% |
| Output increase | 10% |
| Fabric inventory reduction | 40% |
| Trims inventory reduction | 15% |
| Overtime cost reduction | 60% |
| Air freight and penalty reduction | 100% |
| Bottom-line addition (estimated) | ~$4M |
| Working capital reduction (estimated) | ~$3.95M |

# 9.  Key Design Principles for Implementation

The deck implies ten non-negotiable design principles for anyone building or implementing this solution:

- Commit only against realistic critical-resource capacity, checked at sub-category level

- Date quotation must be tool-driven, not memory or experience-driven

- Freeze the plan at the right horizon and protect it from non-essential changes

- Not every delay justifies a plan change; execution buffers exist to absorb disturbances

- Use a single, unified priority mechanism across all work centres and teams

- B >> R > Y > G; no local priority systems allowed

- Control FKD and PCD through mandatory workflow tickets, not through tracking sheets

- Ticket closure must require evidence, not a checkbox

- Schedule laundry with constraint logic, not manual judgement

- Complex multi-machine, lot-based, batch-constrained environments cannot be reliably scheduled by hand

- Prevent manual overrides in the planning visualization layer (FastReact)

- Auto-mode operation preserves the integrity of the load calculation

- Measure performance against first commitments, not revised dates

- Internal reporting must match the customer experience of reliability

- Capture reason codes for every RED order and use them for structured improvement

- POOGI is not optional; it is the mechanism for the system to get better over time

- Integrate with Datatex/ERP to avoid manual data re-entry

- Dual-entry systems degrade data quality and consume bandwidth

- Design for governance, not just functionality

- The system must define who can override a committed date, when firm-zone entry occurs, and what changes are allowed in which zone

# 10.  Open Questions for Planning

The following questions from the deck remain unresolved and must be addressed before detailed system design:

- What is the exact boundary between Vector Flow, FastReact, Datatex, and any Eratex-built platform?

- Will FastReact be retained as the scheduling surface, or will Eratex build its own?

- How will the system technically prevent unauthorised manual plan changes after firm-zone entry?

- How will learning curves for sewing line allocation be calculated and maintained?

- How will capacity buffers be set and updated from historical performance data?

- What is the authoritative source for SMV/SAM — and who maintains it?

- What is the authoritative source for order quantity, shipment splits, and ex-factory commitment?

- How will laundry WIP be captured accurately enough (stage-wise, lot-wise) for daily scheduling?

- Will TMS control only merchandising/pre-production, or also production-release readiness checks?

- Which activities are hard blockers for FKD, PCD, cutting release, sewing loading, and shipment?

- What are the exact dashboard specifications required for daily, weekly, and monthly review routines?

- How will POOGI reason codes be standardised and governed across departments?

# 11.  Closing Synthesis

The Eratex Solution Deck presents a coherent and well-evidenced argument that Eratex's core problem is unreliable flow — not simply poor scheduling. Orders change dates because materials and approvals miss readiness milestones. Critical resources are overloaded unevenly because planning checks only departments, not sub-resource categories. Sewing is reshuffled constantly because execution operates without a stable frozen plan. Laundry is manually scheduled under constraints too complex for manual control. Teams compensate through overtime, outsourcing, inventory, air freight, and management escalation — all of which are symptoms, not causes.

The proposed solution is a closed-loop planning and execution system. Its power is not in any single module but in the integration of all layers: commitment, planning, freezing, execution priorities, pre-production workflow control, laundry scheduling, and improvement routines. Removing or weakening any layer undermines the others.

The solution must be designed and scoped as a closed-loop system: commit only against realistic capacity — freeze the plan — use execution priorities to absorb delays — control FKD and PCD through workflow tickets — schedule laundry with constraint logic — measure and improve through dashboards and reason-code Pareto. Any scope reduction should be made consciously, with explicit acknowledgement of which layer of reliability it weakens.

End of Document